## generated
SPRINT/STORY BOARD
S.No | EPIC ID | SPRINT ID | STORY ID | STORY DESCRIPTION | ASSIGNED TO | ESTIMATED STORY POINTS | STORY PLANNED START | STORY PLANNED END | ESTIMATED EFFORT (IN HRS) | TIME SPENT (IN SECS) | EFFORT CONSUMED (IN HRS) | PENDING EFFORT (IN HRS) | STORY ACTUAL START | STORY ACTUAL END | Story Effort completion % | Story Schedule progress% | Story Schedule Overrun% | Remarks
1 | PCS-28016 | PCS-2124 | PCS-28233 | [ISA8K]: System is allowing more than permitted Licenses | ssubramanian | 4 | 5/20/2021 | 6/17/2021 | 16 | 57600 |  |  | 5/20/2021 | 6/17/2021 |  | 100% | 0%
2 | PCS-28016 | PCS-2124 | PCS-28264 | [ISA8K-F]:Able to establish 25K Tunnels without licenses | ssubramanian | 4 | 5/20/2021 | 6/17/2021 | 16 | 57600 |  |  | 5/20/2021 | 6/17/2021 |  | 100% | 0%
3 | PCS-28322 | PCS-2124 | PCS-28333 | ISA8K Platform porting document-part1 | ssubramanian | 6 | 5/20/2021 | 6/17/2021 | 24 | 86400 |  |  | 5/20/2021 | 6/17/2021 |  | 100% | 0%
4 | PCS-28322 | PCS-2124 | PCS-27371 | SM HW: Licensing Dev Information Documentation | ssubramanian | 4 | 5/20/2021 | 6/17/2021 | 16 | 57600 |  |  | 5/20/2021 | 6/17/2021 |  | 100% | 0%
5 | PCS-28017 | PCS-2124 | PCS-27022 | SuperDoctor: Confirm SuperDoctor diagnostic tool with SM-HW port | rajeshg | 6 | 5/20/2021 | 6/3/2021 | 24 | 64800 |  |  | 5/20/2021 | 6/3/2021 |  | 100% | 0%
6 | PCS-28017 | PCS-2124 | PCS-28232 | [ISA8K]: HW status & other information missing from Admin UI | rajeshg | 4 | 5/20/2021 | 6/3/2021 | 16 | 115200 |  |  | 5/20/2021 | 6/3/2021 |  | 100% | 0%
7 | PCS-28017 | PCS-2126 | PCS-28332 | SM-HW: Pixe Packaging - Testing on HW | rajeshg | 6 | 5/20/2021 | 6/3/2021 | 24 | 10800 |  |  | 5/20/2021 | 6/3/2021 |  | 100% | 0%
8 | PCS-28311 | PCS-2124 | PCS-28312 | QA-ISA8K-Perf Baseline: Max Users/Tunnel Setup count(ESP) | praveens | 4 | 5/4/2021 | 7/13/2021 | 16 | 115200 |  |  | 5/4/2021 | 6/17/2021 |  | 100% | 0%
9 | PCS-28311 | PCS-2124 | PCS-28318 | QA-ISA8K-Perf Baseline: Tunnel setup rate tests(ESP) | praveens | 4 | 5/4/2021 | 7/13/2021 | 16 | 57600 |  |  | 5/4/2021 | 6/17/2021 |  | 100% | 0%
10 | PCS-28311 | PCS-2124 | PCS-28319 | QA-ISA8K-Perf Baseline: Baseline the Max Throughput(ESP) | praveens | 6 | 5/4/2021 | 7/13/2021 | 24 | 86400 |  |  | 5/4/2021 | 6/17/2021 |  | 100% | 0%
11 | PCS-28322 | PCS-2124 | PCS-28441 | [SM-HW]: Investigate the issue where admin UI is not accessible on HW 38 | praveens | 2 | 5/20/2021 | 6/17/2021 | 8 | 50400 |  |  | 5/20/2021 | 6/17/2021 |  | 100% | 0%
12 | PCS-28311 | PCS-2124 | PCS-28313 | QA-ISA8K-Perf Baseline: Max Users/Tunnel Setup count(SSL) | karthikr | 4 | 5/4/2021 | 7/13/2021 | 2 | 115200 |  |  | 5/4/2021 | 6/17/2021 |  | 100% | 0%
13 | PCS-28311 | PCS-2126 | PCS-28315 | QA-ISA8K-Perf Baseline: Baseline the Max Throughput(SSL) | karthikr | 6 | 5/4/2021 | 7/13/2021 | 24 | 28800 |  |  | 5/4/2021 | 6/17/2021 |  | 100% | 0%
14 | PCS-28017 | PCS-2124 | PCS-26807 | SMHW: Checking BIOS configuration | kalaimani.k | 8 | 5/20/2021 | 6/3/2021 | 32 | 28800 |  |  | 5/20/2021 | 6/3/2021 |  | 100% | 0%
15 | PCS-28322 | PCS-2124 | PCS-28334 | ISA8K Platform porting document (Driver related) | kalaimani.k | 6 | 5/20/2021 | 6/17/2021 | 24 | 172800 |  |  | 5/20/2021 | 6/17/2021 |  | 100% | 0%
16 | PCS-28322 | PCS-2124 | PCS-28663 | SM-HW: Analysis and Explore the Secure Boot option on SM HW | kalaimani.k | 4 | 5/20/2021 | 6/17/2021 | 0.33333 | 57600 |  |  | 5/20/2021 | 6/17/2021 |  | 100% | 0%
17 | PCS-28016 | PCS-2124 | PCS-28355 | SM-HW: ISA8000 License parameters information collection | balajit | 6 | 5/20/2021 | 6/17/2021 | 24 | 104400 |  |  | 5/20/2021 | 6/17/2021 |  | 100% | 0%
18 | PCS-28016 | PCS-2124 | PCS-28357 | SM HW: CPU Affinity Usage Checking during traffic | balajit | 6 | 5/20/2021 | 6/17/2021 | 24 | 57600 |  |  | 5/20/2021 | 6/17/2021 |  | 100% | 0%
19 | PCS-28016 | PCS-2124 | PCS-28390 | SM-HW: ISA8000 License checking support | balajit | 4 | 5/20/2021 | 6/17/2021 | 16 | 57600 |  |  | 5/20/2021 | 6/17/2021 |  | 100% | 0%
20 | PCS-28311 | PCS-2126 | PCS-28314 | QA-ISA8K-Perf Baseline: Tunnel setup rate tests(SSL) | balachandras | 6 | 5/4/2021 | 7/13/2021 | 24 | 57600 |  |  | 5/4/2021 | 6/17/2021 |  | 100% | 0%
21 | PCS-28311 | PCS-2126 | PCS-28316 | QA-ISA8K-Perf Baseline: Throughput-Standard/less packet sizes/varied user load(SSL) | balachandras | 8 | 5/4/2021 | 7/13/2021 | 4 | 144000 |  |  | 5/4/2021 | 6/17/2021 |  | 100% | 0%
22 | PCS-28322 | PCS-2124 | PCS-28438 | [SM HW]: Flashing serial number to BIOS | balachandras | 2 | 5/20/2021 | 6/17/2021 | 8 | 57600 |  |  | 5/20/2021 | 6/17/2021 |  | 100% | 0%